## Burndown
Burn Rate
Week 1 | 68
Week 2 | 68
Week 3 | 66
Week 4 | 55
Week 5 | 0

## Completed Tasks
Title | URL | Assignees | Status | Linked pull requests | Sub-issues progress | Size | Story Points | Iteration | Labels | Module/Component | Effort | Risk/Blockers | Test Coverage | Closed | Created | Updated | Priority | Column 1
Design the LLM API Integration Pipeline | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/9 | bellagerken | Done |  |  |  | 4 | Sprint 1 |  | AI Parser |  | Clear |  | 2026-07-12T23:09:19Z | 2026-06-19T14:06:13Z | 2026-07-23T20:31:56Z | High
Wireframe the Interactive Student Dashboard | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/10 | tpedney | Done |  |  |  | 4 | Sprint 1 |  | Frontend UI |  | Clear |  |  | 2026-06-19T14:09:13Z | 2026-08-09T19:56:23Z | High
Design the Core Database Schema for Pace MSCS Catalog | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/7 | Anndeen1 | Done |  |  |  | 4 | Sprint 1 |  | Database |  | Clear |  | 2026-07-12T23:07:44Z | 2026-06-19T14:00:55Z | 2026-07-12T23:07:46Z | High
Architect the Optimization Engine Logic | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/8 | YuRoGameDev | Ready |  |  |  | 4 | Sprint 1 |  | Backend CSP |  | Clear |  |  | 2026-06-19T14:03:35Z | 2026-06-23T19:23:58Z | High
QA/QC of Github Projects Kanban Board | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/4 | starbuckjames | Done |  |  |  | 2 | Sprint 1 |  | Infrastructure |  | Clear |  | 2026-06-18T15:53:54Z | 2026-06-16T20:18:06Z | 2026-06-18T15:53:57Z | High
Draft the Comprehensive Systems Architecture Diagram | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/11 | cvar-ga | Done |  |  |  | 2 | Sprint 1 |  | Documentation |  | Clear |  | 2026-06-21T16:58:58Z | 2026-06-19T14:24:01Z | 2026-06-21T16:58:59Z | High
Provision Accounts | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/12 | cvar-ga | Done |  |  |  | 4 | Sprint 1 |  | Infrastructure |  | Clear |  | 2026-06-21T03:26:58Z | 2026-06-19T14:28:40Z | 2026-06-21T03:27:15Z | High
Sample Data | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/31 |  | Done |  |  |  | 2 | Sprint 1 |  | Database |  | Clear |  | 2026-08-09T20:03:43Z | 2026-07-12T14:02:50Z | 2026-08-09T20:03:44Z
Data Flow Diagram | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/19 |  | Done |  |  |  | 2 | Sprint 1 |  | Documentation |  | Clear |  | 2026-07-12T18:01:01Z | 2026-06-22T21:21:45Z | 2026-07-12T18:01:02Z
ER diagram | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/14 |  | Done |  |  |  | 2 | Sprint 1 |  | Database |  | Clear |  | 2026-07-12T23:07:58Z | 2026-06-22T20:56:30Z | 2026-07-12T23:08:00Z
Feedback Mechanism | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/25 |  | Ready |  |  |  | 3 | Sprint 1 |  |  |  | Clear |  |  | 2026-07-10T14:58:40Z | 2026-07-10T15:23:05Z
Preference Weighting | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/24 |  | Done |  |  |  | 3 | Sprint 1 |  | AI Parser |  | Clear |  |  | 2026-07-10T14:57:55Z | 2026-08-09T22:03:44Z
Transparency / Confidence Flags | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/23 |  | Done |  |  |  | 5 | Sprint 1 |  | AI Parser |  | Clear |  |  | 2026-07-10T14:56:53Z | 2026-08-09T22:03:36Z
Transcript Ingestion | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/22 |  | Done |  |  |  | 5 | Sprint 1 |  | AI Parser |  | Clear |  |  | 2026-07-10T14:55:41Z | 2026-08-09T22:03:24Z
AI Input Extraction | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/20 |  | Done |  |  |  | 8 | Sprint 1 |  | AI Parser |  | Clear | 0 |  | 2026-07-10T14:53:15Z | 2026-08-09T22:03:02Z
Account Picture | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/38 |  | Backlog |  |  |  | 2 | Sprint 2 |  | Frontend UI |  |  |  | 2026-08-11T20:39:47Z | 2026-07-30T21:33:02Z | 2026-08-09T20:39:47Z | High
Upload Transcript Feature | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/39 |  | Done |  |  |  | 2 | Sprint 2 | 4 | AI Parser |  |  |  | 2026-08-03T15:17:56Z | 2026-07-30T21:35:25Z | 2026-08-03T15:17:56Z | High
Generate use case diagram | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/45 | cvar-ga | Done |  |  |  | 2 | Sprint 2 | documentation | Documentation | Low | Clear |  | 2026-08-11T02:29:57Z | 2026-08-11T02:04:42Z | 2026-08-11T02:29:59Z | Low
Course Availability | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/26 |  | Done |  |  |  | 3 | Sprint 2 |  | Database |  |  |  | 2026-08-09T20:03:35Z | 2026-07-10T17:01:03Z | 2026-08-09T20:03:36Z |  | 55
Prerequisite Validation | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/27 |  | Done |  |  |  | 8 | Sprint 2 |  | Database |  |  |  | 2026-08-09T20:03:32Z | 2026-07-10T17:08:13Z | 2026-08-09T20:03:33Z
Student Degree Progress | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/28 |  | Done |  |  |  | 5 | Sprint 2 |  | Database |  |  |  | 2026-08-09T20:03:25Z | 2026-07-10T17:13:46Z | 2026-08-09T20:03:27Z
Manage Course Capacity | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/29 |  | Done |  |  |  | 8 | Sprint 2 |  | Database |  |  |  | 2026-08-09T19:59:28Z | 2026-07-10T17:29:15Z | 2026-08-09T19:59:29Z
Track Academic Progress | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/30 |  | Done |  |  |  | 5 | Sprint 2 |  | Database |  |  |  | 2026-08-09T19:59:15Z | 2026-07-10T18:00:17Z | 2026-08-09T19:59:17Z
User Log In | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/33 |  | Done |  |  |  | 2 | Sprint 2 |  | Frontend UI |  |  |  | 2026-08-09T19:56:43Z | 2026-07-12T23:13:40Z | 2026-08-09T19:56:43Z
Add more errors/constrictions | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/37 |  | Done |  |  |  | 2 | Sprint 2 |  | Frontend UI |  |  |  | 2026-08-09T19:56:35Z | 2026-07-25T18:09:44Z | 2026-08-09T19:56:36Z
Organize CSS files | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/36 |  | Done |  |  |  | 2 | Sprint 2 |  | Frontend UI |  | Clear |  | 2026-08-09T19:56:12Z | 2026-07-25T18:08:52Z | 2026-08-09T19:56:14Z
MUST HAVE DARK MODE | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/42 | starbuckjames | Done |  |  |  | 7 | Sprint 2 | 4 | Frontend UI |  |  |  | 2026-08-02T19:56:03Z | 2026-08-01T23:20:51Z | 2026-08-09T19:56:03Z
Contact Us and Settings Icons On Website | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/41 | starbuckjames | Done |  |  |  | 2 | Sprint 2 | 3 | Frontend UI |  |  |  | 2026-08-01T22:12:35Z | 2026-08-01T22:00:15Z | 2026-08-09T19:56:01Z
EmailJS | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/35 |  | Done |  |  |  | 3 | Sprint 2 |  | Frontend UI |  | Clear |  | 2026-08-09T19:55:52Z | 2026-07-23T22:17:29Z | 2026-08-09T19:55:53Z
Contact Page | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/34 |  | Done |  |  |  | 3 | Sprint 2 |  | Frontend UI |  |  |  | 2026-08-09T19:55:48Z | 2026-07-23T22:14:53Z | 2026-08-09T19:55:50Z
Working Sign Up | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/32 |  | Done |  |  |  | 2 | Sprint 2 | 1 | Frontend UI |  |  | 1 | 2026-07-12T23:12:14Z | 2026-07-12T23:11:44Z | 2026-07-12T23:12:16Z
Accept Form Fields Property | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/40 |  | Done |  |  |  | 2 | Sprint 2 | 4 |  |  |  |  | 2026-08-03T15:17:53Z | 2026-07-30T21:36:56Z | 2026-08-03T15:17:53Z
Merge dev branch with main | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/43 | cvar-ga | Done |  |  |  | 2 | Sprint 2 |  | Infrastructure |  |  |  | 2026-08-11T02:03:42Z | 2026-08-09T22:06:28Z | 2026-08-11T02:03:43Z
User acceptance testing | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/44 | Anndeen1, bellagerken, cvar-ga, starbuckjames, tpedney, YuRoGameDev | Done |  |  |  | 2 | Sprint 2 |  | Frontend UI |  | Clear |  | 2026-08-11T02:29:39Z | 2026-08-09T22:11:03Z | 2026-08-11T02:29:41Z
Ensure data accuracy + performance | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/18 |  | Done |  |  |  | 2 | Sprint 2 |  | Database |  | Clear |  | 2026-08-11T12:51:15Z | 2026-06-22T21:11:35Z | 2026-08-11T12:51:16Z
Check Database interaction with Optimizer | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/16 |  | Done |  |  |  | 2 | Sprint 2 |  | Database |  | Clear |  | 2026-08-11T12:51:25Z | 2026-06-22T21:08:46Z | 2026-08-11T12:51:26Z
Store Data in Database | https://github.com/2026-PaceU-Capstone/intelligent-academic-path-optimizer/issues/15 |  | Done |  |  |  | 2 | Sprint 2 |  | Database |  | Clear |  | 2026-08-11T12:51:31Z | 2026-06-22T21:04:47Z | 2026-08-11T12:51:33Z