## Tasks
Task | Priority | Owner | Status | Story Points | Notes
Project Description | High |  | Completed | 1
Personas | High |  | Completed | 2
Technologies | High | Younes R | Completed | 1
Project Schedule | High |  | Completed | 1
Team Agreement | High |  | Completed | 1
MVP | High | Charles Varga | Completed | 2

## Sprint 0 Burndown Tracking Tabl
Date | Ideal Remaining | Actual Remaining
2026-05-21 | 8 | 8
2026-05-22 | 8 | 8
2026-05-23 | 8 | 8
2026-05-24 | 8 | 8
2026-05-25 | 8 | 8
2026-05-26 | 8 | 8
2026-05-27 | 8 | 8
2026-05-28 | 6 | 6
2026-05-29 | 6 | 6
2026-05-30 | 6 | 6
2026-05-31 | 6 | 6
2026-06-01 | 6 | 6
2026-06-02 | 4 | 4
2026-06-03 | 4 | 4
2026-06-04 | 4 | 4
2026-06-05 | 4 | 4
2026-06-06 | 4 | 4
2026-06-07 | 4 | 2
2026-06-08 | 4 | 2
2026-06-09 | 2 | 2
2026-06-10 | 2 | 2
2026-06-11 | 0 | 2
2026-06-12 | 0 | 0
2026-06-13 | 0 | 0