## Sprint1 User Stories
US_ID | Feature | User Story | Acceptance Criteria | Story Points | Status
US_01 | AI Input Extraction | As a student, I want to describe my academic situation in plain language, so that I can get a recommended schedule without filling out a rigid form. | - A free-text message returns a structured object with program, level, completed courses, and credit limit. - Loosely written codes ("CS 101") are normalized ("CS101"). - The output validates against the shared solver schema. | 8 | Completed
US_02 | Transcript Ingestion | As a student, I want to optionally upload my transcript, so that I don't have to retype every course I've already completed. | - The endpoint accepts optional transcript text alongside the message. - Transcript courses are added as suggestions flagged for confirmation, not treated as authoritative. - PDF text is extracted before processing. | 5 | Not Completed - carried to Sprint 2
US_03 | Transparency / Confidence Flags | As an advisor, I want the system to flag anything the AI assumed or was unsure about, so that the student can confirm it instead of trusting a hidden guess. | - Any default the AI fills in appears in an "assumptions" list. - Fields needing verification appear in "needs_confirmation". - Unmappable input is preserved in "unparsed_notes" rather than dropped. | 5 | Partially Completed - flags produced; confirmation UI carried to Sprint 2
US_04 | Preference Weighting | As a student, I want to state my top priorities (e.g. "focus on ML"), so that the recommended schedule reflects what matters to me. | - Up to 3 priorities are captured, in order of importance. - Priorities are passed to the solver as soft preferences (affect ranking, not validity). | 3 | Not Completed - carried to Sprint 2
US_05 | Feedback Mechanism | As a user, I want to flag incorrect or hallucinated AI output, so that the team can identify and improve weak spots. | - Each result surfaces the assumption/confirmation flags a feedback prompt can use. - A user can submit a flag tied to a specific result. | 3 | Not Completed - carried to Sprint 2
|  |  | Total Story Points | 24