## Tasks
Task | Priority | Owner | Status | Date Complete | Story Points | Notes
Design the LLM API Integration Pipeline | High | bella | Completed | 2026-07-12 | 4
Design the Core Database Schema for Pace MSCS Catalog | High | andeen | Completed | 2026-07-12 | 4
QA/QC of Github Projects Kanban Board | High | James S | Completed | 2026-06-18 | 2
Draft the Comprehensive Systems Architecture Diagram | High | charles | Completed | 2026-06-21 | 2
Provision Accounts | High | charles, younnes | Completed | 2026-06-20 | 4
Functional Sign-up (#32) | High | tara, younnes | Completed | 2026-07-12 | 2
Data Flow Diagram | High | andeen | Completed | 2026-07-12 | 2
ER diagram | High | andeen | Completed | 2026-07-12 | 2
Sample Data | Medium | andeen | In progress |  | 2

## Sprint 1 Burndown Tracking Tabl
Date | Ideal Remaining | Actual Remaining
2026-06-14 | 22 | 24
2026-06-15 | 21.2 | 24
2026-06-16 | 20.5 | 24
2026-06-17 | 19.7 | 24
2026-06-18 | 19 | 22
2026-06-19 | 18.2 | 22
2026-06-20 | 17.4 | 16
2026-06-21 | 16.7 | 16
2026-06-22 | 15.9 | 16
2026-06-23 | 15.2 | 16
2026-06-24 | 14.4 | 16
2026-06-25 | 13.7 | 16
2026-06-26 | 12.9 | 16
2026-06-27 | 12.1 | 16
2026-06-28 | 11.4 | 16
2026-06-29 | 10.6 | 16
2026-06-30 | 9.9 | 16
2026-07-01 | 9.1 | 16
2026-07-02 | 8.3 | 16
2026-07-03 | 7.6 | 16
2026-07-04 | 6.8 | 16
2026-07-05 | 6.1 | 16
2026-07-06 | 5.3 | 16
2026-07-07 | 4.6 | 16
2026-07-08 | 3.8 | 16
2026-07-09 | 3 | 16
2026-07-10 | 2.3 | 16
2026-07-11 | 1.5 | 16
2026-07-12 | 0.8 | 2
2026-07-13 | 0 | 2